## From applicant
Milestone | Timeframe | Title | Description | Fiat amount
1 | 10 weeks | Smart contract development | - Development of Karna's main smart contract for accepting Concordium tokens (CCD) donations. - Development of the DAO-managed wallet smart contract. - Development of campaign smart contract for handling donated funds for approved campaigns. - Development of NFT (Non-Fungible Token) smart contract, including the generation of Volunteer NFTs for registered users and the ability to upgrade NFTs based on genuine volunteer efforts. - Development of the decentralized autonomous organization (DAO) structure, including the ability for DAO members to vote on campaign proposals and platform decisions. | 20000 USD
2 | 6 weeks | Frontend development | - Development of the frontend interface for users to interact with Karna and integration with smart contract backend | 5000 USD
3 | 5 weeks | Wallet integration and testnet | - Integration of Concordium Identity Wallet for users to manage their CCD and NFTs. - Rigorous testing on the testnet to ensure smooth interactions and functionality. - Comprehensive security audits for smart contracts to identify and mitigate vulnerabilities. | 5000 USD
4 | 1 week | Mainnet tests and ready for launch | - Conduct successful tests on the Concordium mainnet, ensuring the platform's stability and security and prepare for the official launch | 0 USD